# European Family Summer Camp — Evidence-Based Founder Feasibility Report

Supplier discovery, two-city bake-off, economics, legal architecture, and paid-demand validation

Prepared from independently checkable public sources. No supplier inquiry, reservation, contract, booking, payment, or private-account access occurred.

# Executive decision

Decision: CONDITIONAL BUILD Do not select a city or collect customer money yet. Run a same-scope written-bid bake-off between the Cascais–Oeiras coast and Porto–Foz–Matosinhos. Porto is the current economic leader; Cascais is the current premium-brand leader. Launch only if legal, supplier, insurance, inventory and paid-demand gates all pass.

The business is plausible, but the proposed late-hours child program is not an off-the-shelf Portuguese camp product. Public camps establish operator supply, retail price anchors, ages and normal hours; none found publishes the proposed 21:30 weekday finish. That gap is the product differentiator and the central execution risk.

Launch window: 4 July–1 August 2027; camp 5–30 July. The July start avoids relying on local primary-school availability before the official 30 June 2027 term end. [S05]

MVP: 18 families, approximately 30 children, ages 6–12, four weeks.

Child schedule: Monday–Thursday 13:30–21:30; Friday 13:30–18:30, with optional late Friday care priced separately.

Operating model: Portuguese RNAVT organizer/merchant of record + IPDJ-registered camp operator + licensed/insured specialist vendors; U.S. brand owns positioning and community.

Demand proof: Paid, fully refundable €250 priority reservations held by a compliant merchant of record. Free waitlists, likes, DMs and Instagram interest do not count.

# What changed after replacing assumptions with public evidence

| Earlier premise | Public discovery finding | Revised decision |
| --- | --- | --- |
| Cascais as predetermined launch city | Central/high-season Cascais retail housing can be far above viable unit economics; Porto has materially lower public 2BR anchors and several group-oriented operators. | Run Cascais and Porto as equal RFP tracks. |
| Late camp treated like a normal supplier quote | Public camps generally finish around 16:00–18:30. No public equivalent to 21:30 was found. | Price the late program bottom-up, then replace it with a custom IPDJ-operator bid. |
| Late-June start | Portuguese public preschool and first-cycle classes run through 30 June 2027. | Start 4 July; camp starts 5 July. |
| Single-apartment listings prove housing | They prove only price points, not 18 units, cluster geography, cancellation terms or July 2027 availability. | Require a unit-by-unit written inventory matrix. |
| Category interest proves demand | Market statistics establish a plausible audience, not willingness to pay €13.9k–€15.4k. | Use paid/refundable reservations and signed contracts. |
| Brand can accept deposits directly | Bundling housing, camp and activities is package-travel sensitive; U.S. seller-of-travel rules can also matter. | No money until fixed-scope Portuguese and U.S. legal review clears fund flow. |

# Evidence standard

Every material input in the financial model is labeled using the following hierarchy:

| Class | Meaning | Permitted use |
| --- | --- | --- |
| Observed | Official law/registry or a public supplier price, schedule, capacity statement or listing. | Can establish existence, legal requirements and a price anchor. It does not establish 2027 availability or negotiated group terms. |
| Derived | Arithmetic built from observed facts, such as staffing ratios, hours, public wages or scenario formulas. | May support a bounded planning range; must be replaced by a written bid before commitment. |
| Estimate | A reasoned range where no exact public analogue exists. | Only acceptable with a hard cap and an identified proof step. |
| Unknown | No reliable public evidence for the exact fact pattern. | Must be resolved before the applicable gate. |

Critical limitation Public discovery can identify capable-looking suppliers and defensible ranges. It cannot verify July 2027 inventory, commercial appetite, custom late-hours delivery, final insurance exclusions, tax treatment or contract enforceability.

# Product definition

| Element | Founding product |
| --- | --- |
| Dates | Arrival Sunday 4 July 2027; camp Monday 5 July–Friday 30 July; departure Sunday 1 August. |
| Families | 18 target; 15 signed-family absolute launch floor. |
| Children | Approximately 30; ages 6–12 only in year one. |
| Core hours | Mon–Thu 13:30–21:30; Fri 13:30–18:30. |
| Meals | Afternoon snack and dinner Mon–Thu; Friday snack and early meal/packed option subject to bid. |
| Housing | Independent 2BR family apartments with kitchen, reliable Wi-Fi, child-safe setup, utilities and cleaning included. |
| Parents | Optional coworking, two adult/community anchors weekly, local orientation, concierge channel and date-night add-on. |
| Families | Opening and closing events, one weekly family activity, curated weekend guides; major weekend excursions optional. |
| Customer promise | Live in Portugal for a month while maintaining an Eastern/Central-compatible or flexible U.S. work schedule. |

## Time-zone truth

Portugal summer time is five hours ahead of U.S. Eastern and eight hours ahead of Pacific. The proposed 13:30–21:30 local window corresponds to approximately 08:30–16:30 Eastern and 05:30–13:30 Pacific. A genuine 09:00–17:00 Pacific workday would require childcare to roughly 01:00 local time and is not a credible mass-market camp promise.

Defensible positioning Do not advertise “work your normal U.S. day from Europe” without qualification. Advertise a product for Eastern/Central schedules, flexible founders, asynchronous professionals and families able to shift work earlier.

# Destination bake-off

| Destination | Weighted score | Role | Public-evidence interpretation |
| --- | --- | --- | --- |
| Cascais-Oeiras Coast | 90.0 | Primary premium RFP track | Strongest premium/partner ecosystem; housing cap is the critical risk. |
| Porto-Foz-Matosinhos | 88.7 | Primary value RFP track | Better economics; good public camp and furnished housing supply; premium positioning and clustered scale require bids. |
| Valencia | 82.1 | Plan C only | Excellent camps but one hour worse U.S. overlap and separate Spanish legal stack not yet researched to Portugal depth. |
| San Sebastian | 74.4 | Premium future cohort | Excellent local camp analogue and strong appeal; expensive constrained housing and weaker airport access. |

The numerical score is a decision aid, not a fact. Cascais and Porto are close enough that supplier bids and paid price conversion should decide the launch city.

## Track A — Cascais–Oeiras coast

Strengths: Lisbon airport, coastal identity, international-school/camp supply, established family destination, premium brand fit.

Weaknesses: High-season housing can destroy margin; central Cascais should not be the footprint assumption.

Procurement zone: Cascais, Estoril, Monte Estoril, Parede, Carcavelos and Oeiras, subject to travel-time limits.

Base housing cap: €3,650 average per 28-night family unit; at least 12 units at or below cap; remaining premium units no more than €4,200 absent repricing.

Custom camp cap: €1,600 per child all-in for the required hours, meals, insurance and core activities.

Public evidence: [S13–S24, S57–S60, S71, S74, S85]

## Track B — Porto–Foz–Matosinhos

Strengths: Lower public furnished-housing anchors, credible university/English/surf camp supply, Atlantic coast, airport/metro access, stronger base economics.

Weaknesses: Premium positioning and clustered family inventory need proof; camp and housing may be geographically dispersed.

Procurement zone: Porto centre/Boavista/Foz, Matosinhos and Leça da Palmeira, with a transport plan.

Base housing cap: €2,500 average per 28-night family unit.

Custom camp cap: €1,500 per child all-in.

Public evidence: [S25–S34, S53, S62–S68, S70, S72–S73, S82–S84, S86]

# Public housing discovery

| Track | Public supplier/listing | Observed public evidence | What it proves / does not prove | Source |
| --- | --- | --- | --- | --- |
| Cascais | BeGuest Cascais Inn | €2,200/month | Single unit; useful low anchor, not July group inventory | S57 |
| Cascais | Parede family apartment | €2,700/30 days | Supports broader coast; single listing | S23 |
| Cascais | Vila Bicuda T1 | €7,140/28 nights at 2026 high-season public retail | 79-villa scale signal; requires major discount | S20–S21 |
| Cascais | Vila Bicuda T2 | €11,620/28 nights at 2026 high-season public retail | Not viable at retail | S20–S21 |
| Cascais | NAMA Carcavelos | 45 planned residences | Potential single-site solution; opening and 2027 availability uncertain | S22 |
| Cascais | Casa de Limão Parede | Three 2BR units; public €300/night | Micro-cluster only; retail far above cap | S74 |
| Porto | Feel Corporate Housing Campanhã | €1,236 average/30 days | Low public anchor; date/scale not proven | S65 |
| Porto | Boavista 2BR | €1,730 average/30 days | Supports Porto base range | S31 |
| Porto | Uniplaces Bonfim 2BR | €1,960 published July 2026 monthly rate | Date-specific historical anchor | S66 |
| Porto | Modern Cedofeita 2BR | €2,800 average/30 days | Upper public benchmark | S30 |
| Porto | Vibrant Host | Eight apartments marketed for groups; public examples | High-priority RFP lead; family rate and inventory unknown | S72 |
| Porto | Oporto Maison | Multiple serviced-apartment buildings; “from” rate public | Cluster lead; July quote required | S33–S34, S86 |

Housing conclusion Porto has the stronger public cost evidence. Neither city has publicly demonstrated an 18-unit July 2027 cluster. A written inventory schedule—not a verbal capacity claim—must list every unit, bedrooms, occupancy, address, walking/transit time, tax, cleaning, utilities, cancellation and payment dates.

# Public camp supplier discovery

| Track | Supplier | Observed public product | Registry status | Interpretation | Source |
| --- | --- | --- | --- | --- | --- |
| Cascais | Camp Go | 08:30–17:30; €60/day | IPDJ 515/DRLVT | Credible operator; custom late bid required | S13,S71 |
| Cascais | Carcavelos Tennis | 08:30–18:00; ~€950/4 weeks | IPDJ 413/DRLVT | Strong normal-hours anchor | S14,S71 |
| Cascais | Prime School | 09:00–16:00; €300/week | SPRINGDOMAIN 410/DRLVT | International fit; no late product | S15,S71 |
| Cascais | King’s Cascais | 08:30–16:30; €290/week | Legal organizer to confirm | Facility/brand option | S16 |
| Cascais | Wave Riders | 09:30–17:30; €235/week | Specialist proof required | Surf component, not sole camp | S85 |
| Porto | U.Porto CDUP | €155/week; food, insurance, sports kit included | IPDJ 253/DRNorte | Excellent low-cost benchmark; daily hours not public | S70,S83 |
| Porto | Surfing Life | 09:00–18:00; €250/week with lunch; paid extensions public | IPDJ 25/DRNorte | High-priority custom-bid candidate | S70,S82 |
| Porto | British Council | Arrival 09:00; pickup by 18:00; €195/week | Underlying organizer to document | English component; late extension required | S84 |
| Porto | Juvigo Multi Camp listing | 08:30–18:30; from €190/week | Marketplace listing only | Useful schedule/price anchor | S68 |

Camp conclusion Public normal-hours retail is roughly €620–€1,200 per child for four weeks, depending on supplier. The proposed late-hours all-in model is estimated at €1,450 Porto / €1,550 Cascais, with hard bid caps of €1,500 / €1,600. These figures are derived, not quotes.

## Custom late-hours camp cost build

| Cost block | Public evidence / derivation | Planning implication |
| --- | --- | --- |
| Staffing | Portuguese law and IPDJ materials require a coordinator and age-based monitor ratios; mixed ages 6–12 create conservative staffing needs. [S01–S03] | Bid must show roster, ratios by activity, employment status and backup coverage. |
| Wages | Portugal’s 2026 minimum monthly wage is €920; qualified bilingual, late-shift staff should be budgeted above minimum. [S69] | Do not base service quality on minimum wage alone. |
| Employer cost | Public Portuguese Social Security guidance lists a 23.75% employer contribution benchmark. [S06] | Camp operator, not U.S. brand, should employ/manage monitors. |
| Meals | Four dinners/week plus snacks materially exceed normal day-camp catering. | Require menu, allergy process, food operator and per-child unit rate. |
| Insurance | Camp personal-accident and operator cover are mandatory/available; hazardous activities need endorsements. [S04,S79–S80] | Insurance must be included in camp bid with certificate and exclusions. |
| Late shift | No public operator publishes the 21:30 finish. | Custom premium and transport/safeguarding plan are unavoidable. |

# Legal and operating architecture

The public-law research indicates a package-sensitive product: accommodation, camp and other travel/tourist services are marketed together at an inclusive price. The exact classification, organizer identity, fund flow and tax treatment require fixed-scope Portuguese advice before any reservation payment.

| Party | Recommended responsibility | Evidence/gate |
| --- | --- | --- |
| U.S. brand company | Brand, marketing, customer insight, community design, partner QA and content. No direct customer fund collection before legal clearance. | U.S. seller-of-travel/privacy advice; Portuguese opinion on marketing/referral boundary. |
| Portuguese RNAVT organizer / merchant of record | Customer contract, package disclosures, funds, refunds, supplier contracts, assistance, tax/TAMS treatment and insolvency/RC framework. | Current RNAVT entry, liability policy, FGVT status and written MoR bid. [S75–S77] |
| IPDJ-registered camp operator | All child programming, staff, ratios, safeguarding, meals, venue, camp insurance, records and emergency operations. | Official registry record, prior communication evidence and complete custom bid. [S02,S70–S71] |
| Specialist vendors | Surf, transport and excursions under their own registrations, qualified staff and insurance. | Certificates, endorsements and contracts in organizer chain. |
| Housing suppliers | Licensed lodging, exact unit inventory, services, safety and cancellation terms. | Unit matrix and registration evidence. |

Public evidence: [S01–S12, S75–S78, S87]

## Public RNAVT discovery

| Candidate | Observed registry/coverage evidence | Current limitation |
| --- | --- | --- |
| Door Travel / D Travel | RNAVT 5243; public registry snapshot showed liability and FGVT information. | Coverage must be current for July 2027; no commercial quote. |
| Travel Store | RNAVT 2229; public registry snapshot. | Renewal timing and MoR appetite unverified. |
| Be In Travel | RNAVT 8116; public registry snapshot. | No quote or appointment. |
| Viagem à Vista | RNAVT 3840; public registry snapshot. | No quote or appointment. |
| Lisboa Sightseeing | Publicly markets DMC/group capability and an RNAVT number. | Official registry, insurance and exact legal entity must be reverified. |

Official public benchmarks show an RNAVT registration fee and an initial guarantee-fund contribution, but those statutory costs do not establish a commercial organizer fee. The model retains an 8%–15% DMC/organizer range and a 10% base cap until same-scope bids arrive. [S75–S77]

# Insurance evidence

| Layer | Public evidence | Decision treatment |
| --- | --- | --- |
| Camp personal accident | Mandatory framework and public historical pricing/coverage examples exist. [S04,S79] | Included in camp bid; policy schedule must cover dates, participants and activities. |
| Camp/operator liability | Public Portuguese tourist-animation/holiday-camp products exist. [S80] | Operator certificate and exclusions required. |
| RNAVT organizer liability/guarantee | Official registry framework requires liability/guarantee protections. [S75–S77] | Organizer must maintain cover through the cohort. |
| U.S. brand GL/E&O | No public quote matches U.S. marketing + minors + Portugal + package-sensitive product. | Model range €2,000–€6,000; must be replaced by bindable underwriting. |
| Surf, motor, food, cyber | Potential exclusions and separate vendor policies. | Each activity/vendor must be specifically scheduled or endorsed. |

Insurance conclusion The statutory camp policy itself is unlikely to be the major cost. The material unknown is cross-border brand/program liability, defense territory, U.S. claim exposure and hazardous-activity exclusions.

# Economics

| Scenario | Families | Revenue | Variable cost | Contribution margin | First-year result | Break-even families |
| --- | --- | --- | --- | --- | --- | --- |
| Cascais low | 18 | €258,800 | €128,536 | 50.3% | €60,264 | 9.7 |
| Cascais base | 18 | €263,400 | €169,273 | 35.7% | €15,627 | 15.0 |
| Cascais high | 18 | €268,000 | €238,260 | 11.1% | –€70,260 | 60.5 |
| Porto base | 18 | €237,600 | €138,000 | 41.9% | €23,100 | 13.8 |

Base-case pricing is a market test, not validated demand: Cascais €13,100 for two adults + one child and €15,400 for a family of four; Porto €11,800 and €13,900 respectively. Airfare and most parent food are outside the program price.

Cascais base: €263,400 revenue, 35.7% contribution margin, €15,627 first-year result and 15-family full first-year break-even.

Porto base: €237,600 revenue, 41.9% contribution margin, €23,100 first-year result and 13.8-family full first-year break-even.

High-cost failure: Cascais at €4,500 housing, €1,850 camp and 15% organizer fee collapses to an 11.1% contribution margin and a €70,260 first-year loss.

Economic rule Do not “make it work” by hiding costs. If same-scope bids push contribution margin below 30%, or if full first-year break-even exceeds 15 signed families, stop or redesign.

# Competitor and substitution pressure

| Alternative | Public signal | Implication |
| --- | --- | --- |
| Roam Collective | Public 2026 evidence indicates a five-week benchmark starting at €8,500 for one adult + one child, with additional-person pricing; Roam also reports a meaningful 2026 cohort. [S38–S39] | Proves category activity but not this product’s price conversion. |
| Boundless Life | Public 2027 Sintra summer pricing starts materially below the proposed family price and includes housing/education/community in the starting package. [S40] | The product must win on late hours, camp experience, community and housing—not merely Portugal. |
| DIY Porto/Cascais | Public housing + normal day camp can be substantially cheaper. | Customer pays for coordination, late hours, community, risk reduction and ready-made peers. |
| Local camps | Retail normal-hours programs are inexpensive. | Late-hours extension is the value driver and cost driver. |

The key commercial question is not whether families like the idea. It is whether enough families will pay the proposed premium over a DIY month and over packaged alternatives.

# Demand evidence and validation

Addressable context: U.S. official statistics show a large population of families with children and working parents, and Census data show a large work-from-home population. [S41–S42]

Pain evidence: Recent Pew research reports meaningful difficulty finding summer care among working parents who need care for ages 6–12. [S43]

What this does not prove: It does not prove international travel intent, four-week availability, willingness to pay, or compatibility with shifted work hours.

## Paid reservation protocol

Complete the legal/MoR fund-flow gate before accepting any payment.

Publish both city concepts with exact dates, hours, inclusions, exclusions, price and refund terms.

Collect a €250 priority reservation that is fully refundable, credited to the program and held/refunded by the compliant merchant of record.

Count only cleared, unique, active customer payments. Exclude staff/founder friends given special terms, duplicates, free signups, survey responses and social engagement.

Required pace: 10 active paid reservations in 30 days; 20 in 60 days; 30–36 in 90 days.

Select the city using written supplier economics plus paid conversion, not founder preference.

Convert to signed program contracts; require at least 15 signed families by 31 January 2027.

Validation rule A free waitlist may help build an audience, but it contributes zero to the launch gate.

# Hard launch gates

| Gate | Pass standard | Deadline logic |
| --- | --- | --- |
| Portuguese legal/tax | Fixed written opinion for package classification, organizer, TAMS/VAT, camp boundary, employment/PE, lodging, minors/privacy and consumer terms. | Before marketing a paid reservation |
| U.S. legal | Written treatment of CA/FL/WA seller-of-travel exposure, refundable reservation collection, privacy and marketing/referral structure. | Before taking money |
| RNAVT/MoR | Current registry, RC policy, FGVT, MoR function, English customer terms, refund SLA and fee ≤10% absent repricing. | Before reservation launch |
| Camp | IPDJ registration; custom full-scope bid; staff/ratios; safeguarding; venue; meals; insurance; transport; emergency plan. | Before selecting city |
| Housing Cascais | 18 units, average ≤€3,650; exact matrix; acceptable clustering/cancellation. | Before material commitment |
| Housing Porto | 18 units, average ≤€2,500; exact matrix; acceptable clustering/cancellation. | Before material commitment |
| Insurance | Bindable cross-border brand/program terms and all vendor certificates/endorsements. | Before sale |
| Economics | Contribution margin ≥35% target, 30% absolute floor; full first-year break-even ≤15 families. | After bid normalization |
| Paid demand | 10/30d; 20/60d; 30–36/90d; ≥15 signed by 31 Jan 2027. | Before nonrefundable inventory |
| Working capital | Nonrefundable supplier exposure fully covered by collected, legally usable customer capital plus reserve. | At every commitment |

# Recommended execution sequence

Issue identical RFPs to the Cascais and Porto camp, housing and RNAVT shortlists.

Commission fixed-scope Portuguese legal/tax review using the included legal brief; in parallel commission U.S. seller-of-travel/privacy review.

Normalize written bids into the workbook. Reject incomplete supplier responses rather than filling gaps with optimism.

Obtain bindable insurance indications for the exact fact pattern and activity set.

Run a legal-compliant paid/reservable two-city price test.

Choose the city only if both its supplier economics and its paid conversion pass.

Secure conditional inventory with staged deposits tied to signed-family thresholds.

Reach 15 signed families by 31 January 2027 or stop.

Run final supplier verification, safeguarding, emergency and customer-onboarding work.

The free work now complete is public discovery: supplier names, public prices, official registration evidence, public law/regulator sources, model ranges and fail gates. The next evidence is inherently non-public and must be generated through written bids, fixed-scope advice, underwriting and paid reservations.

# Founder decision

Current recommendation Proceed to procurement and legal validation, not to launch. Porto is the first economic choice if it can support a coherent family cluster and premium customer experience. Cascais remains viable only if coastal inventory averages at or below €3,650 and the late camp stays at or below €1,600 per child. Select neither if paid demand or legal/safety gates fail.

# Appendix A — Key model inputs

| Category | Input | Low | Base | High | Evidence class | Source |
| --- | --- | --- | --- | --- | --- | --- |
| Cohort design | Families | 18 | 18 | 18 | Design choice | Founder design |
| Cohort design | Children | 28 | 30 | 32 | Estimate | Derived planning range |
| Pricing - Cascais | Base family price (2 adults + 1 child) | 13100 | 13100 | 13100 | Test price | Pricing hypothesis informed by Roam benchmark [S38-S39] |
| Pricing - Cascais | Additional child price | 2300 | 2300 | 2300 | Test price | Derived |
| Pricing - Porto | Base family price (2 adults + 1 child) | 11800 | 11800 | 11800 | Test price | Derived |
| Pricing - Porto | Additional child price | 2100 | 2100 | 2100 | Test price | Derived |
| Housing - Cascais coast | 28-night family unit | 3000 | 3600 | 4500 | Estimate from public inventory | S20-S24,S57-S60,S74 |
| Housing - Porto | 28-night family unit | 1900 | 2400 | 3200 | Estimate from public inventory | S29-S34,S62-S66,S72-S73,S86 |
| Camp - Cascais coast | 4-week normal-hours public retail | 486 | 1000 | 1200 | Observed range | S13-S19 |
| Camp - Porto | 4-week normal-hours public retail | 620 | 780 | 1000 | Observed range | S25-S28,S70,S82-S84 |
| Camp - Cascais coast | Custom late-hours camp all-in | 1350 | 1550 | 1850 | Derived estimate | S01-S06 and supplier range S13-S19 |
| Camp - Porto | Custom late-hours camp all-in | 1250 | 1450 | 1750 | Derived estimate | S01-S06 and S25-S28 |
| Organizer/DMC | Fee on supplier spend | 0.08 | 0.1 | 0.15 | Market estimate | S49-S52 and market benchmark |
| Payment | Blended processing cost | 0.01 | 0.024 | 0.033 | Derived from public pricing | S44-S45 |
| Tax reserve | VAT/TAMS reserve | 0.0075 | 0.015 | 0.03 | Provisional reserve | S07-S08 |
| Customer acquisition | CAC | 600 | 900 | 1500 | Test assumption | Requires paid campaign |
| Community | Events/programming | 350 | 490 | 700 | Estimate from public activities | Municipal and supplier discovery |
| Transfers | Airport transfer allocation | 120 | 150 | 180 | Estimate from public retail | S48 |
| Transit | Local transit allocation | 50 | 60 | 80 | Observed/estimated | S47 |
| Legal | Fixed-scope Portuguese legal/tax review | 3075 | 7500 | 14760 | Derived estimate | S81 plus fixed-scope quote required |
| Legal | U.S. seller-of-travel/privacy review | 3000 | 4000 | 6000 | Estimate | S10-S12 |
| Insurance | Brand/program insurance allocation | 2000 | 4000 | 6000 | Estimate | S04,S79-S80 + written underwriting |

# Appendix B — Public source register

| ID | Category | Source | Type |
| --- | --- | --- | --- |
| S01 | Portugal camp law | Decree-Law 32/2011 - holiday camp organizer regime | Official law |
| S02 | Portugal camp registration | IPDJ - Registration of Holiday Camp Organizers | Official regulator |
| S03 | Portugal camp staffing | IPDJ - Ferias em Movimento program and staffing support benchmarks | Official regulator |
| S04 | Portugal camp insurance | Portaria 629/2004 - mandatory camp insurance minimums | Official law |
| S05 | Portugal school calendar | Despacho 8368/2024 - school calendars through 2027-28 | Official law |
| S06 | Portugal employer costs | Portuguese Social Security - employer contribution 23.75% | Official regulator |
| S07 | EU tourism rules | Your Europe - tourism business, package travel and VAT margin scheme | Official EU |
| S08 | Portugal package travel | Decree-Law 17/2018 - package travel and linked travel arrangements | Official law |
| S09 | EU package travel | European Commission - Package Travel Directive | Official EU |
| S10 | California seller of travel | California Attorney General - Seller of Travel | Official regulator |
| S11 | Florida seller of travel | Florida FDACS - Sellers of Travel | Official regulator |
| S12 | Washington seller of travel | Washington Department of Licensing - Sellers of Travel | Official regulator |
| S13 | Cascais camp supplier | Camp Go 2026 at IPS Cascais | Supplier |
| S14 | Cascais camp supplier | Carcavelos Tennis School - Summer Camp | Supplier |
| S15 | Cascais camp supplier | Prime School Summer Camp 2026 | Supplier |
| S16 | Cascais camp supplier | King's College School Cascais Summer Camp | Supplier |
| S17 | Cascais camp supplier | Shaka Surf Camp Cascais | Supplier |
| S18 | Cascais camp supplier | Anima Park ATL and holiday camps | Supplier |
| S19 | Cascais camp supplier | Oeiras Sports Holiday Program | Municipal program |
| S20 | Cascais housing | Vila Bicuda official site | Supplier |
| S21 | Cascais housing | Vila Bicuda public 2026 high-season retail rate listing | Public reseller |
| S22 | Cascais housing | NAMA House Carcavelos - 45 serviced residences | Supplier/development |
| S23 | Cascais housing | Flatio Parede furnished family apartment | Public listing |
| S24 | Cascais housing | Portugal Portfolio Cascais coast inventory | Property manager |
| S25 | Porto camp supplier | British Council Porto Summer Courses 2026 | Supplier |
| S26 | Porto camp supplier | University of Porto Sports Holiday Camp 2026 | University supplier |
| S27 | Porto camp supplier | Surfing Life Club Porto Kids Camps 2026 | Supplier |
| S28 | Porto camp supplier | CCD Porto Holiday Camps 2026 | Supplier |
| S29 | Porto housing | Flatio Feel Corporate Housing Marques II | Public listing |
| S30 | Porto housing | Flatio Modern 2BR Cedofeita | Public listing |
| S31 | Porto housing | Flatio BoaVista 2BR apartment | Public listing |
| S32 | Porto housing | Flatio VIVA Republica 2BR serviced apartment | Public listing |
| S33 | Porto housing | Oporto Maison serviced apartments | Supplier |
| S34 | Porto housing | Oporto Maison Alves da Veiga apartments | Supplier |
| S35 | Valencia camp supplier | American School of Valencia Summer Program 2026 | Supplier |
| S36 | Valencia camp supplier | Valencia Tennis Academy Summer Camp 2026 | Supplier |
| S37 | Valencia camp supplier | Valencia CF Summer Camp 2026 | Supplier |
| S38 | Competitor | Roam Collective official site | Competitor |
| S39 | Competitor | Roam / ilo published terms | Competitor terms |
| S40 | Competitor | Boundless Life public pricing | Competitor |
| S41 | Demand | BLS - employment in families with children, 2025 | Official statistics |
| S42 | Demand | U.S. Census - work from home inequalities | Official statistics |
| S43 | Demand | Pew - parents' summer childcare difficulty, 2026 | Research |
| S44 | Payments | Stripe Portugal pricing | Supplier |
| S45 | Payments | Stripe U.S. pricing | Supplier |
| S46 | Coworking | Cowork Cascais pricing | Supplier |
| S47 | Transit | MobiCascais fares and passes | Municipal supplier |
| S48 | Transfers | Airport City Transfer Cascais pricing | Supplier |
| S49 | RNAVT/DMC | Lisboa Sightseeing DMC and group services | Supplier |
| S50 | RNAVT/DMC | Portugal Travel Concierge white-label DMC | Supplier |
| S51 | RNAVT/DMC | LIMITS DMC Cascais | Supplier |
| S52 | RNAVT/DMC | Cititravel Portugal DMC | Supplier |
| S53 | Legal pricing | CoreLegal public business legal retainer pricing | Legal supplier |
| S54 | Insurance discovery | Ponto Seguro holiday camp insurance | Insurance broker |
| S55 | Insurance discovery | Generali holiday camp / ATL insurance | Insurer |
| S56 | Insurance discovery | BIS Allianz tourist animation liability insurance | Broker |
| S57 | Cascais housing | BeGuest Cascais Inn 2BR monthly listing | Public listing |
| S58 | Cascais housing | Flatio Estoril Beach Flower 2BR | Public listing |
| S59 | Cascais housing | Flatio Monte Estoril 2BR with pool | Public listing |
| S60 | Cascais housing | Flatio Historical Cascais 2BR | Public listing |
| S61 | RNAVT registry | Official RNAVT 5243 - Door Travel / D Travel | Official registry |
| S62 | RNAVT registry | Official RNAVT 2229 - Travel Store | Official registry |
| S63 | RNAVT registry | Official RNAVT 8116 - Be In Travel | Official registry |
| S64 | RNAVT registry | Official RNAVT 3840 - Viagem a Vista | Official registry |
| S65 | Porto housing | Flatio Campanha 2BR family apartment | Public listing |
| S66 | Porto housing | Uniplaces Bonfim 2BR 2026 monthly listing | Public listing |
| S67 | Valencia camp supplier | Futedu full-day soccer camp | Supplier |
| S68 | Porto camp supplier | Juvigo Porto Multi Camp | Marketplace listing |
| S69 | Portugal wage | Portuguese Government - minimum wage rises to €920 in 2026 | Official government |
| S70 | Portugal camp registry | IPDJ - Registered holiday camp organizers, North region | Official regulator PDF |
| S71 | Portugal camp registry | IPDJ - Registered holiday camp organizers, Lisbon and Tagus Valley | Official regulator PDF |
| S72 | Porto housing | Vibrant Host Solutions - group apartment inventory | Property manager |
| S73 | Porto housing | Porto Touristic Apartments - registered apartment portfolio | Property manager |
| S74 | Cascais housing | Casa de Limão - Parede apartment inventory | Property manager |
| S75 | RNAVT registry | Turismo de Portugal - National Tourism Registry | Official registry |
| S76 | RNAVT registration | ePortugal - RNAVT registration requirements and fee | Official government |
| S77 | RNAVT fund | Turismo de Portugal - Travel and Tourism Guarantee Fund contribution | Official government |
| S78 | EU package travel | Directive (EU) 2026/1024 amending package travel rules | Official EU law |
| S79 | Camp insurance | Ponto Seguro - public holiday-camp personal accident price example | Broker historical price |
| S80 | Tourist animation insurance | BIS - tourist animation insurance public pricing | Broker public price |
| S81 | Legal market pricing | Fixando Portugal - legal services public price guide | Marketplace price guide |
| S82 | Porto camp supplier | Surfing Life Club - schools and youth programs | Supplier |
| S83 | Porto camp supplier | University of Porto CDUP 2026 summer sports camp | University supplier |
| S84 | Porto camp supplier | British Council Portugal - Porto English summer courses | Supplier |
| S85 | Cascais camp supplier | Cascais Wave Riders surf clinics | Supplier |
| S86 | Porto housing | Oporto Maison Entreparedes apartments | Property manager |
| S87 | EU package travel | Your Europe business guidance - package travel | Official EU guidance |