# European Family Summer Camp — Public Supplier Discovery & RFP Pack

Same-scope procurement brief for Cascais–Oeiras and Porto–Foz–Matosinhos

Prepared from independently checkable public sources. No supplier inquiry, reservation, contract, booking, payment, or private-account access occurred.

# Purpose and status

This pack converts public discovery into written-bid requests. It has not been sent. No supplier has quoted, accepted, reserved inventory or been appointed. All respondents must quote the same dates, scope and commercial structure so the two destination tracks can be compared.

Procurement objective Obtain decision-grade written bids for an 18-family, approximately 30-child, four-week July 2027 cohort while preserving the right to stop without material nonrefundable exposure.

# Program fact pattern

| Item | Requirement |
| --- | --- |
| Arrival / departure | Arrival Sunday 4 July 2027; departure Sunday 1 August 2027. |
| Camp dates | Monday 5 July–Friday 30 July 2027; 20 weekdays. |
| Families | 18 target; mix of 3- and 4-person families; approximately 30 children. |
| Children | Ages 6–12 only. |
| Camp hours | Mon–Thu 13:30–21:30; Fri 13:30–18:30. Quote optional Friday extension separately. |
| Locations | Track A: Cascais–Oeiras coast. Track B: Porto–Foz–Matosinhos. |
| Commercial form | All taxes, fees, mandatory insurance and defined services shown separately and as an all-in total. |
| Validity | Bid validity, inventory hold and staged-payment schedule required. |

# RFP 1 — RNAVT organizer / merchant of record

The respondent must be able to serve as the contracting organizer and merchant of record, subject to counsel’s final structure.

| Required response | Evidence / detail |
| --- | --- |
| Legal identity | Full legal name, tax number, address, signatory and ownership. |
| RNAVT | Current number and direct official-registry evidence. |
| Liability / FGVT | Policy certificate, limits, territorial scope, expiry and current guarantee-fund status. |
| Customer contract | English package terms, pre-contract disclosures, cancellation/refund terms, assistance duties, complaint process and force majeure. |
| Fund flow | Ability to collect €250 refundable priority reservations and later program payments; segregated/operating treatment; refund SLA; chargeback handling. |
| Supplier chain | Ability to contract housing, camp, transport, catering and activities as organizer. |
| Tax | Written TAMS/VAT treatment, invoices and treatment of brand/referral/management fee. |
| Fees | Fixed fee and open-book percentage; base model cap 10% of supplier spend. Explain exclusions and minimum fees. |
| References | At least two family/group or educational travel clients. |
| 2027 validity | Commitment to keep registry and policies current through 1 August 2027. |

Automatic disqualifiers No current RNAVT; refusal to show insurance/FGVT evidence; inability to act as merchant of record; unclear refund control; fee structure that cannot be normalized; or reliance on disclaimers instead of organizer obligations.

# RFP 2 — Holiday-camp operator

The bid must cover the complete child program. A normal-hours retail brochure is not responsive.

| Scope | Required bid response |
| --- | --- |
| Operator evidence | Legal entity, tax number, IPDJ registration number, current registry evidence and proof of specific prior-program communication where available. |
| Capacity | 30 children ages 6–12; maximum and minimum viable count; waitlist/backup capacity. |
| Hours | Mon–Thu 13:30–21:30; Fri 13:30–18:30. State exact staff arrival/departure and pickup grace. |
| Staffing | Coordinator, monitor roster assumptions, age-group ratios, qualifications, English level, employment status, background/safeguarding checks, illness/absence backup. |
| Program | Four-week curriculum with sports, arts, local culture, outdoor/beach time and weather backup. No mandatory surf-only specialization. |
| Meals | Snack + dinner Mon–Thu; Friday snack/meal; menus, allergies, food-provider registration and water. |
| Venue | Address, exclusive/shared spaces, toilets, indoor weather capacity, security, accessibility and proximity to housing. |
| Transport | Every movement, licensed carrier, supervision, seatbelts/child restraints, pickup/drop-off and late-hour transport. |
| Safety | Emergency plan, medical lead, incident reporting, missing-child protocol, parent authorization, medication, water/beach procedures. |
| Insurance | Personal accident and liability certificates, limits, exclusions, late hours, beach/surf endorsements and dates. |
| Pricing | All-in per child for 28/30/32 children; one-child and sibling pricing; VAT; payment schedule; cancellation; minimum guarantee. |
| Target cap | Cascais ≤€1,600/child; Porto ≤€1,500/child for complete scope. Quote alternatives if cap cannot be met. |

Automatic disqualifiers No verifiable IPDJ registration; inability to staff statutory ratios; no late-hours safeguarding/transport plan; insurance exclusions for planned activities; unclear legal employer; or price above cap without a product reprice path.

# RFP 3 — Housing cluster

| Requirement | Specification |
| --- | --- |
| Inventory | 18 independent family units for 28 nights. Provide unit-by-unit matrix, not an aggregate claim. |
| Minimum unit | Two real bedrooms, private bathroom, kitchen, dining/work surface, reliable Wi-Fi, heating/cooling appropriate to July and legal occupancy for family size. |
| Services | Utilities, Wi-Fi, arrival clean, mid-stay clean, linens/towels, maintenance SLA, lockout and 24/7 emergency contact. |
| Child suitability | Safe windows/balconies, smoke/CO protection as applicable, stairs/lifts disclosed, cribs/high chairs by request. |
| Location | Address and travel time to camp/coworking. Target: 80% of units within 30 minutes door to door of camp. |
| Licensing | Local lodging/serviced-apartment registration and right to contract group inventory. |
| Price | All taxes, cleaning, utilities, commissions, deposits and damage terms shown per unit and total. |
| Cascais cap | Average ≤€3,650/unit; at least 12 units at/below cap; remaining ≤€4,200 unless customer upgrade revenue is identified. |
| Porto cap | Average ≤€2,500/unit. |
| Payment | No more than 20% nonrefundable exposure before paid conversion gates unless fully covered by customer-backed capital. |
| Cancellation | Staged release dates, name changes, unit substitutions, property failure, re-accommodation and refund terms. |

## Public housing leads

| Track | Lead | Public scale signal | Bid purpose | Source |
| --- | --- | --- | --- | --- |
| Cascais | Vila Bicuda | 79 villas; high public seasonal retail | Test whether a major group discount and T1/T2 mix can meet cap | S20–S21 |
| Cascais | NAMA Carcavelos | 45 residences planned | Test opening certainty, inventory and delivery risk | S22 |
| Cascais | Portugal Portfolio | Managed coastal portfolio | Assemble clustered distributed units | S24 |
| Cascais | Casa de Limão | Three 2BR units | Micro-cluster / premium units | S74 |
| Porto | Vibrant Host | Eight group-oriented apartments | Core cluster lead | S72 |
| Porto | Oporto Maison | Multiple apartment buildings | Core serviced-apartment lead | S33–S34,S86 |
| Porto | Porto Touristic Apartments | Multi-property registered portfolio | Distributed cluster lead | S73 |
| Porto | Boavista Palace | Serviced-apartment format | Cluster/corporate-stay lead | S62 |

# RFP 4 — Insurance broker / underwriter

| Coverage question | Required response |
| --- | --- |
| Named insureds | Proposed U.S. brand, Portuguese organizer, camp operator and additional-insured structure. |
| Territory/jurisdiction | Portugal operations, U.S. customers and claims; defense costs and governing-law limitations. |
| GL/E&O | Limits, deductibles, occurrence/claims-made basis, retro date and professional/travel-program exclusions. |
| Minors | Abuse/molestation, safeguarding, hired/non-owned staff, medical/incident records and exclusions. |
| Activities | Beach, surf, sports, excursions, meals and alcohol-free adult events. |
| Motor | Airport/excursion transport; vendor auto evidence and non-owned exposure. |
| Cyber/privacy | Children’s medical and personal data; breach response. |
| Cancellation | Whether any event cancellation/nonappearance coverage is available and its exclusions. |
| Quote | Bind-able or indication status, premium, taxes, conditions, required risk controls and expiry. |

Planning reserve: €2,000–€6,000 for U.S. brand/program coverage, separate from supplier policies. This is not a quote.

# RFP 5 — Coworking, activities, transfers and catering

| Vendor | Scope | Required proof |
| --- | --- | --- |
| Coworking | 20–30 desks/rotating access, private call rooms, reliable tested bandwidth, local hours, four-week rate. | Business identity, service terms, capacity and backup connectivity. |
| Transfers | Airport and selected excursion transport; family luggage and child restraints. | Operator/license, auto insurance, vehicle/driver list, cancellation and delay plan. |
| Activities | Family opening/closing, weekly family event, adult anchors and optional excursions. | Registration, insurance, capacity, weather/cancellation, all-in group rate. |
| Catering | Camp dinners/snacks and selected events. | Food-business evidence, menu, allergen process, delivery/hot-hold plan, per-head rate. |

# Commercial response template

| Line | Supplier response |
| --- | --- |
| Legal entity / registration |  |
| Service dates / availability |  |
| Capacity / minimum guarantee |  |
| Base price before VAT/tax |  |
| VAT/taxes/mandatory fees |  |
| All-in price |  |
| Deposit / nonrefundable amount |  |
| Payment dates |  |
| Cancellation / attrition |  |
| Substitution / failure remedy |  |
| Insurance evidence |  |
| Bid validity / hold expiry |  |
| Assumptions / exclusions |  |

# Normalized scorecards

| Camp criterion | Weight |
| --- | --- |
| Legal/registry/insurance completeness | 20% |
| Safeguarding and staff quality | 20% |
| Ability to deliver late schedule | 20% |
| Program/meal/venue quality | 15% |
| Price and commercial terms | 15% |
| Location/transport | 10% |

| Housing criterion | Weight |
| --- | --- |
| Exact 2027 inventory and licensing | 25% |
| Average all-in cost | 25% |
| Cluster/travel time | 20% |
| Unit quality/family suitability | 15% |
| Cancellation/payment terms | 10% |
| Operations/SLA | 5% |

| Organizer criterion | Weight |
| --- | --- |
| RNAVT/insurance/FGVT/fund flow | 30% |
| Package/customer/refund capability | 25% |
| Tax/commercial clarity | 15% |
| Supplier contracting/operations | 15% |
| Fee | 10% |
| References | 5% |

# Bid-comparison rule

Reject nonresponsive bids before scoring.

Normalize every quote to the same dates, 18 families and 30 children.

Add omitted taxes, meals, insurance, cleaning, transport and required labor before comparison.

Run the integrated model at 15, 18 and 20 families.

Apply contribution-margin, break-even, working-capital and cancellation gates.

Select neither city if no complete stack passes.

# Public supplier discovery appendix

| Type | Supplier/lead | Observed fact | Source |
| --- | --- | --- | --- |
| Camp | Camp Go | Public 2026 camp; IPDJ registry 515/DRLVT | S13,S71 |
| Camp | Carcavelos Tennis | Public normal-hours pricing; IPDJ 413/DRLVT | S14,S71 |
| Camp | Prime School | Public 2026 program; operator entity IPDJ 410/DRLVT | S15,S71 |
| Camp | U.Porto CDUP | €155/week incl. food/insurance; IPDJ 253/DRNorte | S70,S83 |
| Camp | Surfing Life | €250/week with lunch; IPDJ 25/DRNorte | S70,S82 |
| Housing | Vila Bicuda | 79-villa scale; high public seasonal retail | S20–S21 |
| Housing | NAMA Carcavelos | 45 planned residences | S22 |
| Housing | Vibrant Host | Eight group apartments marketed | S72 |
| Housing | Oporto Maison | Multiple serviced-apartment buildings | S33–S34,S86 |
| Organizer | Official RNT/RNAVT | Public registry and statutory framework | S75–S77 |